## Product_Backlog
Product Name: | MICE Manager | [5 empty] | Complete Fields in Green!!!
Team ID: | Straight Outta Brezeale's 1320
| Team Member Name |  |  |  |  | Initials | Student ID
Required | Chelsea May |  |  |  |  | CM | 1001140094
Required | Jonathan El-Khoury |  |  |  |  | JE | 1001512612
Required | Juan Diego Gonzalez German |  |  |  |  | JDGG | 1001401837
Note: Teams MUST be approved by the Professor (NOT TA) in advance
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 37 |  |  | Total | Total number of features (in column H)
1 | 33 | 4 |  | 1 | Total features left at the end of Sprint #1
2 | 23 | 10 |  | 2 | Total features left at the end of Sprint #2
3 | 15 | 8 |  | 3 | ...and so on
4 | 7 | 8
5 | 3 | 4
6 | 0 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Create a new ice cream flavor | Stock and sell dairy products | picture not yet required, just test the classes here w/o GUI
CC | 2 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new container | Stock and sell dairy products | Picture not yet required
CT | 3 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new topping | Stock and sell better dairy products | Picture not yet required
GUI | 4 | 1 | 8 | 1 | Finished in Sprint 1 | Manager | Use a GUI instead of a terminal | Reduce training costs | This is the main window, with menu bar, tool bar, and optionally status bar
IGUI | 5 | 2 | 13 | 2 | Finished in Sprint 2 | Manager | Use dialogs to create items | Reduce training costs | One dialog should server for all items with minor variations
CS | 6 | 2 | 8 | 2 | Finished in Sprint 2 | Server | Create a serving of ice cream in a container with toppings | Create dairy products to sell | Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and push on a vector
PS | 7 | 2 | 5 | 2 | Finished in Sprint 2 | Customer | Show the components of a serving (container, scoops, and toppings) for verification | Ensure my order was taken correctly
CTM | 8 | 2 | 3 | 2 | Finished in Sprint 2 | Manager | Create a new server | Staff the emporium
CB | 9 | 2 | 2 | 2 | Finished in Sprint 2 | Server | Create a new beloved customer | Keep track of our customers
CO | 10 | 2 | 13 | 2 | Finished in Sprint 2 | Server | Create an order of many servings of ice cream | Serve everyone in a customer party
CSB | 11 | 2 | 1 | 2 | Finished in Sprint 2 | Customer | Create a serving of ice cream in a container with toppings | Self-order and not have to deal with people | This just enables the Customer role to do what the Server can do in defining a serving…
COB | 12 | 2 | 1 | 2 | Finished in Sprint 2 | Customer | Create an order of many servings of ice cream | Self-order and not have to deal with people | ...and order
CE | 13 | 2 | 5 | 2 | Finished in Sprint 2 | Manager | Create an emporium that stocks items and maintains a cash register | Manage the emporium | This includes item stocks, server and customer lists, and the cash register
MST | 14 | 2 | 8 | 2 | Finished in Sprint 2 | Manager | Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled) | Ensure each order is filled and payment collected
SAVD | 15 | 3 | 8 |  | Finished in Sprint 3 | Manager | Save all data to a default file | Ensure our data isn’t lost
LOAD | 16 | 3 | 5 |  | Finished in Sprint 3 | Manager | Load data from a default file | Ensure our data isn’t lost
POS | 17 | 3 | 5 |  | Finished in Sprint 3 | Server | Show the servings in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC | 18 | 3 | 5 |  | Finished in Sprint 3 | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
CM | 19 | 3 | 3 |  | Finished in Sprint 3 | Owner | Create a named manager | Delegate management tasks to a pro
P&L | 20 | 3 | 8 |  | Finished in Sprint 3 | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy
RI | 21 | 3 | 5 |  | Finished in Sprint 3 | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
PIX | 22 | 3 | 21 |  | Finished in Sprint 3 | Customer | Add and display pictures for each item (container, ice cream flavor, and topping) | Better understand the menu
RTM | 23 | 4 | 8 |  | Finished in Sprint 4 | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members
ETMS | 24 | 4 | 8 |  | Finished in Sprint 4 | Manager | Change a server salary | Offer promotions and pay bumps to motivate our team members
AI | 25 | 4 | 8 |  | Finished in Sprint 4 | Server | Restock items (ice cream flavor, container, and topping) | Ensure we can fill every order
RO | 26 | 4 | 8 |  | Finished in Sprint 4 | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 27 | 4 | 5 |  | Finished in Sprint 4 | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
EF | 28 | 4 | 8 |  | Finished in Sprint 4 | Manager | Edit an ice cream flavor | Improve our data and keep it synced to reality
EC | 29 | 4 | 8 |  | Finished in Sprint 4 | Manager | Edit a container | Improve our data and keep it synced to reality
ET | 30 | 4 | 8 |  | Finished in Sprint 4 | Manager | Edit a new topping | Improve our data and keep it synced to reality
ROA | 31 | 5 | 3 |  | Finished in Sprint 5 | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
SALL | 32 | 5 | 5 |  | Finished in Sprint 5 | Owner | Save all data to a specified file | Franchise my company
LALL | 33 | 5 | 5 |  | Finished in Sprint 5 | Owner | Load data from a specified file | Franchise my company
CENEW | 34 | 5 | 13 |  | Finished in Sprint 5 | Owner | Create a new franchise | Franchise my company
XI | 35 | 6 | 21 |  | Finished in Sprint 6 | Manager | Retire an item (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu
XT | 36 | 6 | 13 |  | Finished in Sprint 6 | Manager | Suspend a server (no longer allow their selection for an order or restock, but keep in reports) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 37 | 6 | 5 |  | Finished in Sprint 6 | Manager | Restore a server | Add a former team member tack into service

## Sprint_01_Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2017-10-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-10-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 7 | 4
Day 2 Left | 5 | 2
Day 3 Left | 3 | 2
Day 4 Left | 1 | 2
Day 5 Left | 0 | 1
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CF | JE | Create Container class | Completed Day 1
2 | CT | JE | Create Topping Class | Completed Day 3
3 | CC | JE | Create Flavor Class | Completed Day 3
4 | CS | CM | Create Storefront class | Completed Day 2 | To push containers, toppings, and flavors onto vectors
5 | GUI | CM | Create Main Window GUI | Completed Day 4
6 |  | JDGG | Create Controller Class | Completed Day 2
7 |  | JDGG | Create Main | Completed Day 4
8 |  | JDGG | Create Tool bar | Completed Day 5
9 |  | CM | Create UML Diagram | Completed Day 1
10 |  | JDGG | Create Sequence Diagram | Completed Day 1
11 |  | JE | Create Use Case Diagram | Completed Day 1
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_02_Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2017-10-26 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 11 | 0
Day 2 Left | 11 | 0
Day 3 Left | 10 | 1
Day 4 Left | 6 | 4
Day 5 Left | 2 | 4
Day 6 Left | 2 | 0
Day 7 Left | 2 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | IGUI | JDGG | Converted command line create items to dialogs | Completed Day 3
2 | CS | JE | Make a serving with a container, scoops, and toppings | Completed Day 4
3 | PS | JE | Create a to_string method to see components of serving | Completed Day 4
4 | CTM | JDGG | Create a new server (server.cpp) | Completed Day 4
5 | CO | CM | Create state.h | Completed Day 4
6 | CB | JDGG | Create a new beloved customer (customer.cpp) | Completed Day 5
7 | CO | CM | Create order.cpp | Completed Day 5
8 | CSB | JE | Self-order serving | Completed Day 5
9 | COB | CM | Make several orders for a group | Completed Day 5
10 | CE | JDGG | Make an emporium | In Work
11 | MST | CM | Managing the state of the order | In Work
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_03_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 11 | 0
Day 2 Left | 9 | 2
Day 3 Left | 9 | 0
Day 4 Left | 7 | 2
Day 5 Left | 5 | 2
Day 6 Left | 3 | 2
Day 7 Left | 3 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | CM | Create save method | Completed Day 2
2 |  | CM | create load method | Completed Day 4
3 |  | CM | create a named manager | Completed Day 5
4 |  | JDGG | show servings in order to server | Completed Day 5
5 |  | JDGG | show servings in order to customer | Completed Day 6
6 |  | JDGG | add test_data method | Completed Day 2
7 |  | JE | make an emporium | Completed Day 4
8 |  | JE | managing state of an order | Completed Day 6
9 |  | JE | create profit and loss report | In Work
10 |  | CM | create inventory report | In Work
11 |  | JDGG | create menu with pictures | In Work
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_04_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-16
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 7 | 1
Day 2 Left | 5 | 2
Day 3 Left | 4 | 1
Day 4 Left | 3 | 1
Day 5 Left | 1 | 2
Day 6 Left | 0 | 1
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | CM | Add server report to controller | Completed Day 3
2 |  | JDGG | change a server's salary | Completed Day 1
3 |  | JDGG | restock items | Completed Day 5
4 |  | JDGG | add a order report | Completed Day 2
5 |  | CM | Add a customer report | Completed Day 2
6 |  | JE | edit a container | Completed Day 4
7 |  | JE | edit a scoop | Completed Day 6
8 |  | JE | edit a topping | Completed Day 5
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_05_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-16 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 4 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | CM | Add an order history report
2 |  | JE | save all data to a specified file
3 |  | JDGG | load all data to a specified file
4 |  | JDGG | ask user for file name to franchise company
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_06_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-11-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-11-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 3 | 0
Day 2 Left | 1 | 2
Day 3 Left | 0 | 1
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  | CM | Retire an item | Completed Day 3
2 |  | JDGG | Suspend a server | Completed Day 2
3 |  | JE | Restore a server | Completed Day 2
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84